## Sheet1
Task | Start Date | End Date | Days
Research
Research Databanks for Genomes | 2020-09-07 | 2020-09-14 | 8 | Start | 44075
Research of Coronvirus Taxonomy | 2020-09-07 | 2020-09-14 | 8 | End Sem 1 | 44204
Khan Academy - DNA structure and replication | 2020-09-12 | 2020-09-17 | 6
Research Papers on COVID-19 & Coronaviruses | 2020-09-16 | 2020-10-02 | 17 | End Sem 2 | 44317
Khan Academy - RNA and protein synthesis | 2020-10-23 | 2020-10-25 | 3
Khan Academy - Biotechnology | 2020-12-28 | 2021-01-03 | 7
Research Molecular Docking | 2021-01-08 | 2021-01-17 | 10
Needleman-Wunsch Algorithm | 2021-03-10 | 2021-03-12 | 3
Smith-Waterman Algorithm | 2021-03-15 | 2021-03-16 | 2
SRA Database & FASTQ files | 2021-03-15 | 2021-04-04 | 21
Development
Deploy Gitlab and commence Data Pipeline | 2020-10-12 | 2020-10-16 | 5
GC & AT Content | 2020-10-16 | 2020-10-16 | 1
Protein Syntheses (Genomes DNA -> mRNA -> Protein Outputs) | 2020-10-23 | 2020-10-25 | 3
Normalised Frequency Scores | 2020-10-26 | 2020-11-01 | 7
Nucleotide Composition Analysis | 2020-11-01 | 2020-11-03 | 3
Cluster Analysis (PCA, t-SNE & Seaborn) | 2020-11-01 | 2021-04-04 | 155
Docker Container for installing Python libraries | 2020-11-13 | 2020-11-18 | 6
Standard Functions | 2020-11-18 | 2020-11-18 | 1
Application for Kelvin-2 | 2020-11-18 | 2020-11-20 | 3
Multiple Sequence Alignment Visualisation | 2020-11-04 | 2021-01-14 | 72
Alignments | 2020-01-08 | 2020-01-12 | 5
Molecular Docking | 2021-01-15 | 2021-01-17 | 3
Structural Analysis & Skeletal Diagrams | 2021-02-04 | 2021-02-04 | 1
Visualise Protein-Ligand Interactions | 2021-02-04 | 2021-02-04 | 1
Testing | 2021-02-15 | 2021-04-08 | 53
API | 2021-03-12 | 2021-03-13 | 2
Needleman-Wunsch Algorithm | 2021-03-12 | 2021-03-24 | 13
Smith-Waterman Algorithm | 2021-03-17 | 2021-03-24 | 8
Dissertation
Introduction and Problem Area | 2020-10-02 | 2021-02-04 | 126
Appendix G - Virology | 2020-12-14 | 2020-12-28 | 15
Mathematics - Pairwise Sequence Alignment (Abstract) | 2021-01-01 | 2021-01-03 | 3
Mathematics - Normalised Frequency | 2021-01-04 | 2021-01-08 | 5
Mathematics - Turing Machine modelling Ribosome | 2021-01-05 | 2021-01-29 | 25
Implementation | 2021-01-05 | 2021-04-07 | 93
System Evaluation & Experimentation | 2021-01-05 | 2021-04-07 | 93
Conclusion | 2021-01-18 | 2021-04-08 | 81
System Requirements and Specification | 2021-01-29 | 2021-02-09 | 12
Appendices | 2021-01-29 | 2021-04-05 | 67
Design | 2021-02-20 | 2021-02-21 | 2
Implications | 2021-02-28 | 2021-03-01 | 2
Cluster Analysis - Interpretation | 2021-03-04 | 2021-03-04 | 1
Success Summary | 2021-03-09 | 2021-04-06 | 29
Mathematics - Pairwise Sequence Alignment (DP) | 2021-03-29 | 2021-04-01 | 4
User Feedback - Google Form | 2021-03-05 | 2021-04-12 | 39
Testing | 2021-04-05 | 2021-04-05 | 1
Developed Improvements | 2021-04-06 | 2021-04-06 | 1
Significance of Results | 2021-04-07 | 2021-04-07 | 1